## ProjectMonitoring
Programme | Batch | 2022 - 2026 | Project: | A Novel Community and Family Centric Healthy Meal Planner Integrating Nutritional Information, User Preferences, and Regional Context
B.Tech CSE | Group | 22 | Names: | Rohan Banerjee,Sasshtik Trivedi,Sanjit Dutta,Sibele Pal
Attendance (Insert below names)
Date | Project discussions |  |  |  | Semester | Deliverable | Issues | Guide's remark | Rohan | Sasshtik | Sanjit | Sibele
2025-06-19 | Topic discussion and understanding the project idea |  |  |  | 7 | Finalized project title and domain | Broad problem definition | Topic approved; focus on health, family, and regional context | Present | Present | Present | Present
2025-06-26 | Exploring project domains and sorting potential project topics |  |  |  | 7 | List of possible project ideas | Difficulty in identifying suitable and multilingual datasets | Suggested use of Kaggle and public food/nutrition datasets | Present | Present | Present | Present
2025-07-12 | Discussion related to problem statement formulation |  |  |  | 7 | Draft problem statement | Datasets contained extra and inconsistent characters | Data cleaning and preprocessing required | Present | Present | Present | Present
2025-07-22 | Discussion on what to do in the selected topic and defining objectives |  |  |  | 7 | Final problem statement and objectives | Overlapping scope with existing systems | Emphasize novelty through community and family-centric approach | Present | Present | Present | Present
2025-07-31 | Discussion related to selected datasets and system flow |  |  |  | 7 | Selected dataset and initial workflow design | Review of workflow required | Workflow needs further refinement | Present | Present | Present | Present
2020-08-11 | Pros and cons analysis of datasets and finalizing workflow |  |  |  | 7 | Final dataset selection and refined workflow | Recommendation logic needs validation | Compare approaches and improve logic | Present | Present | Present | Present
2025-08-25 | Synopsis discussion and approval |  |  |  | 7 | Final project synopsis | Prototype planning pending | Literature review to be enhanced | Present | Present | Present | Present
2025-09-14 | Mid-term deliverables discussion |  |  |  | 7 | Partial implementation of recommendation logic | Integration of modules incomplete | Continue implementation and integration | Present | Present | Present | Present
2025-10-25 | Implementation of recommendation logic |  |  |  | 7 | Created a baseline model using Matrix Factorization that determines "What food does an user usually like?". Also applying several constraints that filters, scores and ranks food items accordingly. | Food recommendation based on user's Family information (Family Centric) is yet to be developed. | Develop the Model as a Family Centric Food Recommendation System. | Present | Present | Present | Present
2025-11-20 | Integration and functional testing |  |  |  | 7 | Integrated along with Advanced Modelling Techniques to determine the User Food Sequence with Transformer and Attention Mechanisms. The model was able to generate Ranked and Region-based recommended food. | The System is not yet able to recommend a Whole Meal Plan for a particular user. | Develop the system so that it can generate a whole meal plan for the user. | Present | Present | Present | Present
2025-12-07 | Documentation and report structuring |  |  |  | 7 | Draft final report | Methodology explanation needs clarity | Improve documentation and diagrams | Present | Present | Present | Present
2025-12-19 | Final review and semester-end discussion |  |  |  | 7 | End-semester submission with working prototype | None | Approved for 7th semester completion | Present | Present | Present | Present
Total | [8 empty] | 100% | 100% | 100% | 100%
Overall | [8 empty] | 100% | 100% | 100% | 100%
Guide's signature:
(When maintained on hard-copy)

## Questions
Area | Question | Raised By | Status (Open / Closed) | Response | Response By
Topic Discussion | What topic should be selected? | PD Ma'am | Closed | Health-aware, community-centric meal planning system finalized. | Team
Topic Research | What research gap exists? | Team and PD Ma'am | Closed | Existing systems ignore health, safety, and family context. | Team
Dataset | What datasets are required? | PD Ma'am | Closed | Nutrition, health, food safety, and interaction datasets identified. | Team
Problem Statement | What is the core problem? | PD Ma'am | Closed | Lack of integrated health-centric and family-level meal planning. | Team